## FAR Tracker
Minute Item No | Date of Meeting | Theme | Action | Paper No | Owner | Update | Status
7 | 19/05/2021 and 08/09/2021 | Risk Update | Clinical and Health and Wellbeing risks to be discussed at the next Public Health and Wellbeing Governance Committee meeting, and thereafter the Chief Executive and Chair of the PHWG Committee to have a further discussion. | Paper 14/21 | Jane James | Agreed that proposal be taken to FARC that future risk updates for the Board and Committees sould include, for information, non-corporate COVID portfolio risks. Update following FARC on 17/11/21 Proposal agreed. | Completed
3 | 2021-06-23 | Annual Report and Accounts 2020/21 | Once the annual report and accounts are approved an executive summary to be placed on the PHS website. | Paper 18/21 | Laura Howard | Once accounts are public this will be added to website | Ongoing
3 | 2021-06-23 | Annual Report and Accounts 2020/21 | A pre meeting to be arranged next year with the internal/external auditors. | Paper 18/21 | Laura Howard | Will be underaken for 21/22 accounts - Governance team to arrange meeting prior to the June 2022 FARC meeting with internal/external auditors. | Ongoing
3 | 2021-06-23 | Annual Report and Accounts 2020/21 | Gender Balance: discussion to take place with Scottish Government around compliance. | Paper 18/21 | Laura Howard | Will be underaken for 21/22 accounts. This will be raised at the next SG Technical Accounting Group (TAG) ahead of issuing the annual Accounts manual for 2021/22. Meeting date to be confirmed. | Ongoing
4 | 2021-06-23 | Committee Annual Report 2021 (CCF) | The CCF to be included in the annual reports next year as part of the committee reporting process. | Paper 19/21 | Laura Howard | Will be included next year. | Ongoing
5 | 2021-09-08 | 2021/22 Quarter One Report | Minor amendments to be made to the content of the paper as highlighted in the meeting. | Paper 20/21 | Tim Andrew | Updated in line with agreed amendements, | Completed
5 | 2021-09-08 | 2021/22 Quarter One Report | For future reports, delivery plan section provide more granularity around the amber and red risks | Paper 20/21 | Tim Andrew | Report amended to reflect comments made. | Completed
5 | 2021-09-08 | 2021/22 Quarter One Report | Definition of a complaint and a concern to be provided | Paper 20/21 | Tim Andrew | Completed. Email detailing the definition of a complaint and a concern circulated to Board | Completed
5 | 2021-09-08 | 2021/22 Quarter One Report | Deep Dive of Contact Tracing to be included on agenda for October Development session | Paper 20/21 | Executive & Governance Team | Completed - on agenda for Board development session scheduled for 6 October 2021. | Completed
5 | 2021-09-08 | 2021/22 Quarter One Report | Further clarity on the role and value of Public Health Scotland; involvement in for example programmes of work (e.g assurance, strategic input, etc); | Paper 20/21 | Tim Andrew | Report amended to reflect comments made. | Completed
5 | 2021-09-08 | 2021/22 Quarter One Report | rationale in respect of the prioritisation of partnerships; | Paper 20/21 | Tim Andrew | Report amended to reflect comments made. | Completed
5 | 2021-09-08 | 2021/22 Quarter One Report | Clarity around current and upcoming challenges and any impact; | Paper 20/21 | Tim Andrew | Report amended to reflect comments made. | Completed
5 | 2021-09-08 | 2021/22 Quarter One Report | SLT paper on COP26 to be adapted and shared with the Board | Paper 20/21 | Nick Phin | Completed - on agenda for Board Meeting on 24 November 2021 | completed
6 | 2021-09-08 | Strategic Planning Process | sit rep to be provided to the November meeting | Paper 21/21 | Tim Andrew/Vicki Bibby | Completed. Paper on agenda for Board meeting on 24 November 2021. | Completed
6 | 2021-09-08 | Strategic Planning Process | Further update to be provided to the November meeting | Paper 21/21 | Tim Andrew/Vicki Bibby | Completed - on agenda for Board Meeting on 24 November 2021 | Completed
6 | 2021-09-08 | Strategic Planning Process | review the board planning cycle to ensure meetings happen in a certain order – governance infrastructure is supporting and aligned with this practice | Paper 21/21 | Executive & Governance Team | Forward programme of meetings being produced. Consideration being given to known conflicting priorities for the coming year. Requirement for meetings to be undertaken in a certain order taken on board. | Ongoing
7 | 2021-09-08 | Workforce Planning | Updated Workforce Plan to be reviewed by Board in February 2022 | Paper 22/21 | Vicki Bibby | On forward programme for Board meeting in February 2022 | Ongoing
9 | 2021-09-08 | National Care Service | Item on National Care Service to be included ion Development Session agenda | Paper 24/21 | Executive & Governance Team | Completed - on agenda for Board development session scheduled for 6 October 2021. | Completed
9 | 2021-09-08 | CEO Update | Briefing note on Programme of Change to be shared with the Board | Verbal update | Communications | Completed - briefing note shared 09/09/21 | Completed